## General Status
Date | Robot Alpha | Robot Bravo | Robot Charlie | Robot Delta | Robot Echo
2016-10-06 | Conducting an initial health check. Gripper twitches and gets stuck in "Going in" state | Conducting an initial health check. Seems to be working fine in terms of mechanics and electronics. | Conducting an initial health check. Mechanically operational. | Conducting an initial health check. Delta's battery holder is different from the others. Spend some time making sure everything is electrically sound before moving on. | Conducting an initial health check. Does not seem to be functioning properly. See the documentation JSP left for clues
2016-10-07 | No updates | No updates | Note from JSP: "The robot has issues with its IMU sensor. The heading values from the IMU sensor seems to stick to wrong values. I already replaced the IMU several times, but it didn’t make any change. Consider replacing the wiring and the Arduino Due." | Battery system is pretty similar to the others, but not as easy to use. The behavior is a little different than the others I observed, and the LCD display looks like it is displaying hex-values as opposed to the typical state descriptors I have seen on the others. | Note from JSP: "The robot Echo has issues with its two wheel motors. It accelerates to much faster speed compared to other robots, and this doesn’t seem like software issue. Consider replacing the whole wheel motor assembly. Make sure that the capacitor on the wheel motors are correct ones. Also make sure that the wiring is correct."
2016-10-11 | Recompiled software for both the Due and Fio boards, and the robot still initiates in the Going In state and stays stuck there. | Seems to work well, but the battery connection is really finnicky. | Behavior seems dominated by incorrect readings from the capacitive sensors. Also, the IMU seems broken, as it only returns values between 255 and 305 degrees when rotating it in a full circle. | No updates | Recompiled software for both the Due and Fio boards, and the robot still initiates in the Going In state and stays stuck there.
2016-10-13 | No updates | Digs well but does not back up well | No updates | Digs well but does not back up well | No updates
2016-10-14 | No updates | Running due code and it still works :) upload fio code next time you're in the lab | No updates | Seems to get stuck now? | Testing IMU and noticed that the G value is near -4.6.
2016-10-17 | Reuploaded code that successfully runs on Charlie, and it still gets stuck in Going In mode. TEST_DRIVE_MOTORS demonstrates that the motors work | Nearly perfect behavior. If it hits a front wall while in the Going Out state, it gets stuck there. It will just keep turning, reversing if it hits a wall, or doing donuts if it is near the charging/dumping station. | No updates | Reuploaded code that successfully runs on Charlie, and it still gets stuck in Going In mode. TEST_DRIVE_MOTORS demonstrates that the motors work | No updates
2016-10-20 | PixyCam not providing output? | No updates | No updates | No updates | No updates
2016-10-30 | Updated the firmware on the pixycam and now it is working. The right motor had a lot of loose hot glue on it, and i think it is creating a lot of resistance. Might need to replace the right motor. The pixycam can have its local parameters for colors and communication wiped by improper power supply, and I think the struggling right motor causes in increase in power draw which in turn wipes the Pixy memory. | No updates | No updates | No updates | No updates
2016-11-04 | No updates | Power Board got fried on when Andi was showing me the oscilloscope. | No updates | No updates | Played with the motor parameters and got it working. Need to tune the capacitive sensors and the PID controller. Perhaps update the vision?
2016-11-09 | No updates | Breadboard is working now. Waiting for the 9V and 12V regulators. When the 5V regulated power supply goes to the Arduino we see | No updates | No updates | Updated vision and moved the 3.3V which powers the IMU from the power distribution board directly to the Due
2016-11-10 | Seems to be working fine now...?? Need to tune the PID | Breadboard 5V to power distribution board is acting funny. E-mailed JSP about it, and want to have Bahni take a look at it when she is feeling better | I transplanted the broken power board from Bravo to Charlie, and managed to get it working. The left motor grind loudly - needs replacing. | No updates | No updates
2016-11-11 | No updates | I took the power board from from Charlie, and now Bravo works. This means that there is an issue with the board, not the other on-board hardware. The capacitive sensor and goingIn heading need tuning | No updates | The 5V regulator which goes to the Power Distribution Board is fried. I think it must have shorted on one of the screw beneath it. Make sure to add tape to all of the Power Boards! | No updates
2016-11-13 | Increased Kd and reduced BASE_SPEED and now it follows the pheromone trail better | Everything is good! Need to tune/fix the capacitive sensor | No updates | No updates | Moved the 3.3V which powers the IMU from the Due baord back to the power distribution board.
2016-11-15 | No updates | Fixed capacitor panel and increased surface area covered. Need to calibrate | Replaced motor. IMU still not working | No updates | No updates
2016-11-16 | No updates | No updates | Added an extension to the IMU cables and now it works? Okay. Also, the 5V and 3.3V power lines were wrong, the charging rod wasn't connected, and the Pixy RX/TX lines were flipped. Next step is to fix the Force sensors on the gripper. | No updates | No updates
2016-11-17 | No updates | No updates | The voltage divider wiring on the force sensors were flipped. Now on to the IMU hanging issue. | No updates | No updates
2016-11-18 | No updates | No updates | Ground connection was lost on the capacitive sensor. This hangs the SCL/SDA communication bus, so all readings hang...Solved! Now on to the pixy. The power wires on this were incorrect, so the camera might be fried. try a new one. | No updates | No updates
2016-11-28 | No updates | No updates | Camera returns incorrect data more often than not. Communication issue? I tried a different Pixy Cam, and the issue persisted, so now I think that there might be an issue with the arduino itself? | Power distribution board is fine. Check the wiring on things related to the 5V line on the PB. | No updates
2016-11-30 | No updates | No updates | No updates | I have found that by unplugging the Gripper Servo wires from the Power Distribution Board, the robot operates as normal. Emailed JSP to ask if he has seen this before. | No updates
2016-12-01 | No updates | No updates | No updates | Changed which set of pins were connected to the Gripper Servo and now things seem to be working fine. I also replaced the battery pack and Delta is more agile now. Also calibrated the IMU. | No updates
2016-12-04 | The lower left hall effect sensor wires are broken. Robot still functional. Moved the 5V for Pixy from the PDB to the Arduino 5V pin. Hoping that this line is better regulated, and will prevent the Pixy from wiping the memory so frequently. | No updates | No updates | No updates | No updates
2016-12-07 | No updates | No updates | No updates | No updates | No updates
2016-12-12 | No updates | Increased the panel size | No updates | No updates | No updates
2016-12-13 | Increased the panel size | Wires going to the left force resistive sensor are broken. | Increased the panel size | Increased the panel size | Increased the panel size
2016-12-14 | Fixed the disconnected hall effect sensor | Fixed disconnected wires. Note that this may be a recurring issue on this robot. | Resoldered a connection on the PB. | No updates | No updates
2016-12-15 | No updates | No updates | Changed battery pack | Changed battery pack | No updates
2016-12-16 | No updates | No updates | Reverted battery pack change | Reverted battery pack change | No updates
2016-12-19 | Magnetometer is working now | No updates | No updates | Magnetometer is working now | No updates
2016-12-20 | No updates | No updates | No updates | No updates | Needs new IMU
2017-01-03 | No updates | No updates | No updates | No updates | May not need to replace IMU now that a new calibration technique has been implemented.
2017-01-07 | Need to print out another motor mount bracket. | No updates | No updates | No updates | No updates
2017-01-09 | No updates | Need to print out another motor mount bracket. | No updates | No updates | No updates
2017-01-10 | No updates | New motor bracket installed. Seems to be better than the previous version. | Need to connect wires going to FSR | No updates | No updates
2017-01-11 | No updates | No updates | Fixed wire | No updates | No updates
2017-01-12 | No updates | Loose wire on gripper | No updates | No updates | Left motor wire broken.
2017-01-16 | Changed motor brackets | Fixed wires | Changed motor brackets | Changed motor brackets | Changed motor brackets and fixed motor wires.
2017-01-17 | No updates | No updates | No updates | Fixed broken wires going to the Hall Effect sensors. | No updates
2017-02-05 | No updates | No updates | Fixed gripper | No updates | No updates
2017-02-07 | Check the current sensor. | No updates | No updates | Pixy is now on Due 5v. | I can make this reset by stalling the motors.
2017-02-26 | No updates | Fix broken wires going to Hall effect sensor | Fix broken wires going to Hall effect sensor | No updates | No updates
2017-02-27 | No updates | Fix broken wires going to Hall effect sensor and address the broken wires leading to the capacitive sensor panels. | No updates | Fix broken wires going to Hall effect sensor and address the broken wires leading to the capacitive sensor panels. | No updates
2017-03-01 | Updated with new PDB | Updated with new PDB | Updated with new PDB | Updated with new PDB | Updated with new PDB
2017-07-08 | New motors added. Need to confirm other systems are working. | Needs to be reassembled. Bravo was scrapped heavily during the redesign of Rquad | No updates | Needs new motor bracket | Needs new shell skeleton
7/112017 | No updates | No updates | No updates | No updates | No updates
2017-07-17 | No updates | No updates | No updates | Changed the motor bracket out. | No updates

## Sheet1
PixyCam | 5V | GND | RX1 | RX2
LCD | 3.3V | GND | TX2
Hall Effect Sensors | 5V | GND
Force Sensitive Sensors | 5V | GND | Comm
Gripper Servo | 5V | GND | Comm
Pitch Servo | 5V | GND | Comm
Capacitive Sensro | 3.3V | GND | SCL | SDA
MAG3110 | 3.3V | GND | SCL | SDA
IMU | 3.3V | GND | SCL | SDA
Motor Board | 3.3V | GND | O1A | O2A | O1B | O2B | I1A | I2A | I1B | I2B
SDA | SCL

## Testing
Test Item | Method to run | Robot Alpha | Robot Bravo | Robot Charlie | Robot Delta | Robot Echo
Contact Switches | TestSwitches and TestCapacitors
Drive Motors | TestDriveMotors
Servos | TestServoMotors
IMU | TestIMU
Pixy | TestCamera
IR range | TestIRSensors - Not implemented?
Gripper Sensor | TestGripperSensor - Not implemented?
Digital Proximity | TestDigitalProximity - Implemented?
Relay | TestPowerRelay
Wireless Data
Manual Control
Read Battery Voltage | TestPowerSensors
Read Current Sensor | TestPowerSensors
Charging Detector | Run GoingCharging()
Self Reset | *unplug i2c*

## Inventory
Item | Vendor | Part # | Qnty/Robot | Price | Associated Software
Force Sensitive Resistor - Square | Sparkfun | SEN-09376 | 2 | 7.95 | Please look at CheckPayload() function in the main code. There is no dedicated function for testing this sensor, but CheckPayload() function can be used to test this sensor.
Hall Effect Sensor | DigiKey | OH090U | 4 | 1.67
Magnetometer - MAG3110 | Sparkfun | SEN-12670 | 1 | 14.95 | Please look at MAG3110.cpp and MAG3110.h for the code. To test the sensor, search “for magnetometer MAG3110 sensor test and calibration” in the setup in the main code, and enable that section.
Capacitive Touch Sensor Breakout - MPR121 | Sparkfun | SEN-09695 | 1 | 6.95 | Please look at CapacitiveSensor.cpp, CapacitiveSensor.h, and mpr121.h for the code. To test this sensor, search to “for capacitive sensor test and calibration” in the setup in the main code, and enable that section. In addition, go to FioWirelessV4.ino file, and then enable “enable this part when calibrating/testing the capacitive sensor” section, and then disable “disable this part when calibrating/testing the capacitive sensor” section. This should display the capacitive sensor reading from one pin to the LCD screen.
TapeCase Silver Aluminum Foil Tape with Conductive Acrylic Adhesive, 6yd Length, 1.5'' Width | Amazon | - | 2 | 12.24 | N/A
TapeCase 1.5-6-1181 Copper/Acrylic Adhesive, Foil Tape with Conductive Adhesive, 1.5''x 6 yd | Amazon | - | 1 | 37.01 | Connected to the Capacitive Touch Sensor Breakout - MPR121
Pololu Ball Caster with 1'' Plastic Ball and Ball Bearings | Pololu | 2692 | 2 | 6.95
HS-5485HB Servo, Stock Direction, Increased Rotation | Servocity | 35485S10 | 2 | 34.99
Servo Screws are prone to damage, use with care. Replacements of the same length do not exist. | Replacements of shorter length can be bought at servocity
SparkFun Serial Enabled 16x2 LCD - Black on Green 3.3v | Sparkfun | LCD-09066 | 1 | 24.95
Transistor - NPN (2N3904) | Sparkfun | COM-00521 | 2 | 0.5
Parallel Connection Round 3x 3.7V 18650 Battery Plastic Holder Box | Amazon |  | 1 | 7.17